## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Belajar Project | 10 days | May 24, 2016 8:00 AM | June 6, 2016 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Project Preparation | 1 day | May 24, 2016 8:00 AM | May 24, 2016 5:00 PM |  | 2 | This phase provides initial planning and preparation for the project. Although each project has its own unique objectives, sco
3 | Yes | Auto Scheduled | Project Charter | 1 day | May 24, 2016 8:00 AM | May 24, 2016 5:00 PM |  | 3 | The purpose of this deliverable is to clearly and explicitly define the objectives of the proposed project, analyze all possib
4 | Yes | Auto Scheduled | Prepare Project Charter Document and Identify Stakeholders | 1 day | May 24, 2016 8:00 AM | May 24, 2016 5:00 PM |  | 4 | Prepare Project Charter Document: ...
5 | Yes | Auto Scheduled | Kick-Off Meeting | 0 days | May 24, 2016 5:00 PM | May 24, 2016 5:00 PM |  | 3 | The purpose of this deliverable is to kick-off the project/phase and ensure that all needed information is shared with the res
6 | Yes | Auto Scheduled | Perform Kickoff Meeting | 0 days | May 24, 2016 5:00 PM | May 24, 2016 5:00 PM | 4 | 4 | The purpose of this activity is to gather the whole project team, including all remotely involved resources, to kick-off the p
7 | Yes | Auto Scheduled | Business Blueprint | 9 days | May 24, 2016 5:00 PM | June 6, 2016 5:00 PM |  | 2 | The purpose of this phase is to create/update the business blueprint, which is a detailed process-oriented and technical docum
8 | Yes | Auto Scheduled | Detailed Design - Business Blueprint | 9 days | May 24, 2016 5:00 PM | June 6, 2016 5:00 PM |  | 3 | The purpose of this deliverable is to design, in detail, the to-be business process down to activity level and to describe gap
9 | Yes | Auto Scheduled | Interview grab data and Analysis | 0 days | May 24, 2016 5:00 PM | May 24, 2016 5:00 PM | 2 | 4
10 | Yes | Auto Scheduled | Create Business Requirement Document | 9 days | May 25, 2016 8:00 AM | June 6, 2016 5:00 PM | 9 | 4
11 | Yes | Auto Scheduled | Obtain Business Blueprint Sign-off | 0 days | June 6, 2016 5:00 PM | June 6, 2016 5:00 PM | 8 | 3 | The purpose of this activity is to achieve a formal sign-off of the business blueprint. ...

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Project Manager | P | Work |  |  |  |  | 100% | Rp0.00/h | 0
2 | System Analyst | S | Work |  |  |  |  | 100% | Rp0.00/h | 0
3 | Customer | C | Work |  |  |  |  | 100% | Rp0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Prepare Project Charter Document and Identify Stakeholders | Project Manager | 0 | 8h | 0%
Perform Kickoff Meeting | Project Manager | 0 | 0h | 0%
Interview grab data and Analysis | System Analyst | 0 | 0h | 0%
Create Business Requirement Document | System Analyst | 0 | 72h | 100%
Obtain Business Blueprint Sign-off | Customer | 0 | 0h | 0%