## Project Cost analysis
Project Name | Score Dashboard |  | Cost Performance Index
Project A | 0.1 |  | 1.1
Data Time | Cum Cost | ETC ( estimate to complete) ( estimasi biaya yg diperlukan utk dpt selesai )
Baseline Cost ( total cost perkiraan awal) | 83114563
Estimate at completion (total cost yg diperlukan) | 75709393.7273
Actual cost & Estimate cost to complete | 52809901 | 22899492.7273
Data yg hrs di isi
| ACWP | 52809901 | Actual Cost of Work Performed
| BCWS | 83114563 | Budgeted Cost of Work Performed
| EVM | 57925121 | Earned Value Management atau BCWP (Budgeted Cost of work Performed)
| BAC | 69199128 | Budget At Completion (baseline Cost yg plng pertama)
| Baseline Cost X ( valid baseline cost) | 83114563 | Baseline cost yg plng valid
| CPI | 1.1 | =EVM/ACWP | Cost Performance Index
| SPI | 0.7 | =EVM/BCWS | Schedule Performance Index
| EAC | 75709393.7273 | =ACWP + (Baseline cost X - EVM)/CPI | Estimation At Completion
| VAC | 69199128 | =BAC-EAC | Variance At Completion
| ETC | 22899492.7273 | =EAC-ACWP | Estimate to Complete
PMBOK5 | EAC forecast for ETC work performed at the budgeted rate. | 64083908 | =ACWP + (BAC-EVM)
PMBOK5 | EAC forecast for ETC work performed at the present CPI. | 62908298.1818 | =BAC/CPI
PMBOK5 | EAC forecast for ETC work considering both SPI and CPI factors. | 67451468.5325 | =ACWP + (BAC - EVM)/ (CPI*SPI)
MS Project Formula | EAC | 75709393.7273 | =ACWP + (Baseline cost X - EVM)/CPI | baseline cost pertama dgn baseline "X" terakhir yg dipakai, ada beda cukup jauh