## Summary-time management
Project Time Management- Knowledge area
Project Management Knowledge area description | Plan Schedule Management | Define Activities | Sequence Activities | Estimate Activity Resources | Estimate Activity Durations | Develop Schedule | Control Schedule
Inputs | Project Management Plan | Schedule management plan | Schedule management plan | Schedule management plan | Schedule management plan | Schedule management plan | Project management plan
Inputs | Project charter | Scope baseline | Activity list | Activity list | Activity list | Activity list | Project schedule
Inputs | Enterprise environmental factors | Enterprise environmental factors | Activity attributes | Activity attributes | Activity attributes | Activity attributes | Work performance data
Inputs | Organizational process assets | Organizational process assets | Milestone list | Resource calendars | Activity resource requirements | Project schedule network diagram | Project calendars
Inputs |  |  | Project scope statement | Risk register | Resource calendars | Activity resource requirements | Schedule data
Inputs |  |  | Enterprise environmental factors | Activity cost estimates | Project scope statement | Resource calendars | Organizational process assets
Inputs |  |  | Organizational process assets | Enterprise environmental factors | Risk register | Activity duration estimates
Inputs |  |  |  | Organizational process assets | Resource breakdown structure | Project scope statement
Inputs |  |  |  |  | Enterprise environmental factors | Risk register
Inputs |  |  |  |  | Organizational process assets | Project staff assignments
Inputs | [5 empty] | Resource breakdown structure
Inputs | [5 empty] | Enterprise environmental factors
Inputs | [5 empty] | Organizational process assets
Tools & Techniques | Expert judgment | Decomposition | Precedence diagramming method (PDM) | Expert judgment | Expert judgment | Schedule network analysis | Performance reviews (Trend analysis,Critical path method ,Critical chain method ,Earned value management)
Tools & Techniques | Analytical techniques | Rolling wave planning | Dependency determination | Alternative analysis | Analogous estimating | Critical path method | Project management software
Tools & Techniques | Meetings | Expert judgment | Leads and lags | Published estimating data | Parametric estimating | Critical chain method | Resource optimization techniques
Tools & Techniques |  |  |  | Bottom-up estimating | Three-point estimating | Resource optimization techniques (resource leveling, resource smoothing) | Modeling techniques
Tools & Techniques |  |  |  | Project management software | Group decision-making echniques | Modeling techniques (what if scenario analysis,simulation) | Leads and lags
Tools & Techniques |  |  |  |  | Reserve analysis | Leads and lags | Schedule compression
Tools & Techniques | [5 empty] | Schedule compression (Crashing, Fast Tracking) | Scheduling tool
Tools & Techniques | [5 empty] | Scheduling tool
Tools & Techniques
Tools & Techniques
Tools & Techniques
Tools & Techniques
Tools & Techniques
Output | Schedule management plan | Activity list | Project schedule network diagrams | Activity resource requirements | Activity duration estimates | Schedule baseline | Work performance information
Output |  | Activity attributes | Project documents updates | Resource breakdown structure | Project documents updates | Project schedule | Schedule forecasts
Output |  | Milestone list |  | Project documents updates |  | Schedule data | Change requests
Output | [5 empty] | Project calendars | Project management plan updates ( Schedule baseline,Schedule management plan,Cost baseline)
Output | [5 empty] | Project management plan updates ( Schedule baseline,Schedule management plan,Cost baseline) | Project documents updates (schedule data, project schedule,risk register)
Output | [5 empty] | Project documents updates (Activity resource requirements,Activity attributes,Calendars,Risk register) | Organizational process assets updates

## Map 1
Topics
Level 0 | Level 1 | Level 2 | Level 3
Project Time Management
Plan Schedule Management
Input
Project management plan
Project charter
Enterprise environmental factor
Organizational process asset
tools
Expert judgment
Analytical techniques
Meetings
Output
Schedule management Plan
Define activities
Input
Schedule management
Scope baseline
Enterprise environmental factor
Organizational process asset
tools
Decomposition
Rolling wave planning
Expert judgment
Output
Activity list
Activity attributes
Milestone list
Sequence Activities
Input
Schedule management
Activity list
Activity attributes
Milestone list
Project scope statement
Enterprise environmental factor
Organizational process asset
tools
Precedence diagramming
Dependency determination
Leads and lags
Output
Project schedule network
Project documents updates
Estimate activity resource
Input
Schedule management plan
Activity list
Activity attributes
Resource calendars
Risk register
Activity cost estimates
Enterprise environmental factors
Organizational process assets
tools
Expert judgment
Alternative analysis
Published estimating data
Bottom-up estimating
Project management software
Output
Activity resource requirements
Resource breakdown structure
Project documents updates
Estimate activity duration
Input
Schedule management plan
Activity list
Activity attributes
Activity resource requirements
Resource calendars
Project scope statement
Risk register
Resource breakdown structure
Enterprise environmental factors
Organizational process assets
tools
Expert judgment
Analogous estimating
Parametric estimating
Three-point estimating
Group decision-making echniques
Reserve analysis
Output
Activity duration estimates
Project documents updates
Develop Schedule
Input
Schedule management plan
Activity list
Activity attributes
Project schedule network diagram
Activity resource requirements
Resource calendars
Activity duration estimates
Project scope statement
Risk register
Project staff assignments
Resource breakdown structure
Enterprise environmental factors
Organizational process assets
tools
Schedule network analysis
Critical path method
Critical chain method
Resource optimization techniques (resource leveling, resource smoothing)
Modeling techniques (what if scenario analysis,simulation)
Leads and lags
Schedule compression (Crashing, Fast Tracking)
Scheduling tool
Output
Schedule baseline
Project schedule
Schedule data
Project calendars
Project management plan updates ( Schedule baseline,Schedule management plan,Cost baseline)
Project documents updates (Activity resource requirements,Activity attributes,Calendars,Risk register)
Control Schedule
Input
Project management plan
Project schedule
Work performance data
Project calendars
Schedule data
Organizational process assets
tools
Performance reviews (Trend analysis,Critical path method ,Critical chain method ,Earned value management)
Project management software
Resource optimization techniques
Modeling techniques
Leads and lags
Schedule compression
Scheduling tool
Output
Work performance information
Schedule forecasts
Change requests
Project management plan updates ( Schedule baseline,Schedule management plan,Cost baseline)
Project documents updates (schedule data, project schedule,risk register)
Organizational process assets updates

## Sheet1
Project Time Management- Knowlwedge area
| 6.1 Plan Schedule Management | 6.2 Define Activities | 6.3 Sequence Activities | 6.4 Estimate Activity Resources | 6.5 Estimate Activity Durations | 6.6 Develop Schedule | 6.7 Control Schedule
.1 Inputs | .1 Project management plan .2 Project charter .3 Enterprise environmental factors .4 Organizational process assets | .1 Schedule management plan .2 Scope baseline .3 Enterprise environmental factors .4 Organizational process assets | .1 Schedule management plan .2 Activity list .3 Activity attributes .4 Milestone list .5 Project scope statement .6 Enterprise environmental factors .7 Organizational process assets | .1 Schedule management plan .2 Activity list .3 Activity attributes .4 Resource calendars .5 Risk register .6 Activity cost estimates .7 Enterprise environmental factors .8 Organizational process assets | 1 Schedule management plan .2 Activity list .3 Activity attributes .4 Activity resource requirements .5 Resource calendars .6 Project scope statement .7 Risk register .8 Resource breakdown structure .9 Enterprise environmental factors .10 Organizational process assets | .1 Schedule management plan .2 Activity list .3 Activity attributes .4 Project schedule network diagrams .5 Activity resource requirements .6 Resource calendars .7 Activity duration estimates .8 Project scope statement .9 Risk register .10 Project staff assignments .11 Resource breakdown structure .12 Enterprise environmental factors .13 Organizational process assets | .1 Project management plan .2 Project schedule .3 Work performance data .4 Project calendars .5 Schedule data .6 Organizational process assets
.2 Tools & Techniques | .1 Expert judgment .2 Analytical techniques .3 Meetings | .1 Decomposition .2 Rolling wave planning .3 Expert judgment | .1 Precedence diagramming method (PDM) .2 Dependency determination .3 Leads and lags | .1 Expert judgment .2 Alternative analysis .3 Published estimating data .4 Bottom-up estimating .5 Project management software | .1 Expert judgment .2 Analogous estimating .3 Parametric estimating .4 Three-point estimating .5 Group decision-making techniques .6 Reserve analysis | .1 Schedule network analysis .2 Critical path method .3 Critical chain method .4 Resource optimization techniques .5 Modeling techniques .6 Leads and lags .7 Schedule compression .8 Scheduling tool | .1 Performance reviews .2 Project management software .3 Resource optimization techniques .4 Modeling techniques .5 Leads and lags .6 Schedule compression .7 Scheduling tool
.3 Outputs | .1 Schedule management plan | .1 Activity list .2 Activity attributes .3 Milestone list | .1 Project schedule network diagrams .2 Project documents updates | .1 Activity resource requirements .2 Resource breakdown structure .3 Project documents updates | .1 Activity duration estimates .2 Project documents updates | 1 Schedule baseline .2 Project schedule .3 Schedule data .4 Project calendars .5 Project management plan updates .6 Project documents updates | .1 Work performance information .2 Schedule forecasts .3 Change requests .4 Project management plan updates .5 Project documents updates .6 Organizational